## Summary
BathRemodelHub — Tracking Tracker
Project: BathRemodelHub ¦ Date: 2026-05-05 ¦ Owner: Growth Team / Priyan (Tech)
Metric | Count | Status
Total Pages | 2 | —
Service Landing Pages | 1 | Single-vertical (bath)
Pages with Thumbtack Widget | 1 | ✅ /results.html (RFW iframe popup)
Tracking Params Captured | 0 | ❌ None wired to dataLayer/results yet
Tracking Params Missing | 9 | ❌ utm_source, utm_campaign, utm_facebook_click_id, utm_rt_ad, sub1, source_id, gclid, ttclid, ScCid
Redtrack Offers Confirmed | 0 | ❓ Pending setup
Redtrack Offers Pending | 1 | ❓ Bath Remodel offer
Redtrack Postback URL Registered | 0 | ⚠️ Pending
Open Action Items | 8 | 5 High · 3 Medium
Sheets in this workbook:
1. Summary — quick health overview (this sheet)
2. Page List — every page with Stage + Production URLs
3. UTM Mapping — which UTM/click params are captured per page
4. Redtrack Offers — full offer URLs for stage and prod
5. Tracking Params — current parameter dictionary
6. Action Items — open work, owners, priority
7. Analytics Stack — platforms and what they track

## Page List
Page List — Stage & Production URLs
Every BathRemodelHub page with full URLs for both environments
# | Service / Page | Slug | Page Type | Stage URL | Production URL | Thumbtack Widget / CTA
1 | Home | / | Home / Landing | https://stage.bathremodelhub.us/ | https://bathremodelhub.us/ | ZIP capture → /results.html
2 | Results | /results.html | Listing + Widget | https://stage.bathremodelhub.us/results.html | https://bathremodelhub.us/results.html | ✅ Thumbtack RFW (iframe popup)
3 | Bath Remodel | / (default) | Service Landing | https://stage.bathremodelhub.us/ | https://bathremodelhub.us/ | Same as Home — single-vertical site

## UTM Mapping
UTM & Click ID Mapping Per Page
Status of each tracking parameter on each page (current state, before Redtrack wiring)
# | Page (Slug) | utm_source | utm_campaign | utm_facebook_click_id | utm_rt_ad | sub1 | source_id | gclid | ttclid
1 | Home (/) | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | ❌
2 | Results (/results.html) | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | ❌
Note: | Currently no Redtrack/UTM params are read from the URL or pushed to dataLayer. Mirroring HouseCrew, wire these up in quotes-api.js and results.html (window.brhTracking) and forward them to backend/result links.

## Redtrack Offers
Redtrack — Offer URLs by Service
Stage + Production offer URLs, ready to paste into Redtrack
# | Service | Status | Stage Offer URL | Production Offer URL | Notes
1 | Bath Remodel (Home) | ❓ Pending | https://stage.bathremodelhub.us/?sub1={clickid}&utm_campaign={rt_cid}&utm_facebook_click_id={sub11}&utm_rt_ad={sub2}&zipcode={sub3}&utm_source=cma-growthfusion&source_id=gf1 | https://bathremodelhub.us/?sub1={clickid}&utm_campaign={rt_cid}&utm_facebook_click_id={sub11}&utm_rt_ad={sub2}&zipcode={sub3}&utm_source=cma-growthfusion&source_id=gf1 | Create in Redtrack; verify zipcode case + register postback URL

## Tracking Params
Tracking Parameters Dictionary
Every parameter we plan to capture (or are missing) and how it should flow
Parameter | Source | Captured Where (Target) | Passed To (Target) | Status
sub1 | Redtrack {clickid} | quotes-api.js · results.html | window.brhTracking, result links | ❌ Not yet wired
utm_campaign | Redtrack {rt_cid} | quotes-api.js · results.html | window.brhTracking, result links | ❌ Not yet wired
utm_facebook_click_id | Redtrack {sub11} | quotes-api.js · results.html | window.brhTracking, result links | ❌ Not yet wired
utm_rt_ad | Redtrack {sub2} | quotes-api.js · results.html | window.brhTracking, result links | ❌ Not yet wired
utm_source | Hardcoded in offer | quotes-api.js · results.html | window.brhTracking, backend API | ⚠️ Default 'cma-growthfusion' is sent server-side, but URL value is not yet read
source_id | Hardcoded in offer | quotes-api.js | Result links | ❌ Not yet wired
zipCode / zipcode | Redtrack {sub3} or user input | results.html | window.brhTracking, API call | ⚠️ User input works; URL passthrough needs case-tolerant handling (zipcode vs zipCode)
gclid | Google Ads | — | — | ❌ Not captured
ttclid | TikTok Ads | — | — | ❌ Not captured
ScCid | Snapchat Ads | — | — | ❌ Not captured
utm_content | TBC | — | — | ❌ Not captured — confirm if needed

## Action Items
Open Action Items
Open work to bring BathRemodelHub tracking to parity with HouseCrew
# | Item | Owner | Priority | Status | Notes
1 | Capture Redtrack click params (sub1, utm_campaign, utm_facebook_click_id, utm_rt_ad, source_id) on landing → store in window.brhTracking and forward to /results.html | Tech (Priyan) | High | Open | Mirror HouseCrew quotes-api.js / results.html implementation
2 | Forward window.brhTracking values into POST /api/businesses utmData | Tech | High | Open | Backend already accepts utmData.utm_source; extend or pass through full utmData object
3 | Append tracking params to outbound result/CTA links and to the RFW iframe URL | Tech | High | Open | Append to iframeEl.src so Thumbtack receives attribution
4 | Create Redtrack offer for Bath Remodel (stage + prod) and register postback URL | Growth | High | Open | See 'Redtrack Offers' sheet for ready URLs
5 | Configure GTM Page Hostname trigger filter (only fire on bathremodelhub.us / stage.bathremodelhub.us) | Growth/Tech | High | Open | Currently fires on any host; will pollute analytics on localhost
6 | Capture and forward gclid (Google Ads), ttclid (TikTok), ScCid (Snapchat) for paid media attribution | Tech | Medium | Open | Add to brhTracking schema and forward links
7 | Normalize zipcode vs zipCode casing in URL parsing | Tech | Medium | Open | Be case-tolerant; backend expects zipCode in JSON body
8 | Decide on utm_content usage and document in Tracking Params sheet | Growth | Medium | Open | Confirm with media team

## Analytics Stack
Analytics & Tracking Stack
Platforms in use (or planned) and what each tracks
Platform | Status | Container / Account | Tracks | Notes
Google Tag Manager (GTM) | ✅ Live | GTM-M8VC8STX | All client-side events (Search, CompareQuoteOpen, QuoteSubmitted) | Loaded in frontend/index.html. Add hostname filter for production/stage only.
Thumbtack Partner API | ✅ Staging | Client ID bb119518-… (staging) | Server-side keyword and business search calls | Switch to prod creds (1cc4638b-…) before launch
Thumbtack RFW (Request Flow Widget) | ✅ Live | Embedded iframe on /results.html | Quote submissions inside the popup | URL is rewritten from staging-partner.thumbtack.com → thumbtack.com on open
Redtrack | ❓ Pending | — | Click attribution (Facebook, Google, TikTok, Snapchat clicks → leads) | Need offer + postback registered; see 'Redtrack Offers' and 'Action Items'
trkfy.us track.js | ✅ Loaded | https://tk.trkfy.us/track.js | External tracking pixel (loaded in frontend/index.html) | Confirm purpose with Growth team
Google Ads (gclid) | ❌ Not wired | — | Google Ads click attribution | Capture gclid in brhTracking and forward
Meta / Facebook Ads | ⚠️ Partial | utm_facebook_click_id slot reserved | Facebook click ID via Redtrack {sub11} | Wire alongside other Redtrack params
TikTok Ads (ttclid) | ❌ Not wired | — | TikTok click attribution | Capture ttclid
Snapchat Ads (ScCid) | ❌ Not wired | — | Snapchat click attribution | Capture ScCid